## Sheet1
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Sprint | Epic Link | Epic Name | Epic Status | Epic Color | Flagged | Epic/Theme | Story Points | Business Value | Rank
TrojanHorse | TROJ-2398 | 耀汉做完M24石狮子wild之后，修改其元素动画 | Task | To Do | Major | Unresolved | dongtao | xuchengkai | xuchengkai | 01/Dec/17 12:36 PM |  | 01/Dec/17 12:36 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9419
TrojanHorse | TROJ-2419 | 新机器元素动画-M6水晶鞋主题 | Task | To Do | Major | Unresolved | dongtao | xuchengkai | xuchengkai | 01/Dec/17 1:36 PM |  | 01/Dec/17 1:36 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9437
TrojanHorse | TROJ-2471 | M25淘金热机器炸弹TNT的效果可以调整 | Task | To Do | Major | Unresolved | dongtao | Zhao Yunlong | xuchengkai | 04/Dec/17 11:51 AM |  | 04/Dec/17 3:41 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9492
TrojanHorse | TROJ-2451 | 检查applovin插页式广告展示为何为0 | Bug | To Do | Critical | Unresolved | fanrongqi | Zhao Yunlong | Zhao Yunlong | 01/Dec/17 8:30 PM |  | 01/Dec/17 8:30 PM |  |  | 1.20.1 |  |  | 0 | 1 | _thumb_13215.png | [15 empty] | None | [8 empty] | 9471
TrojanHorse | TROJ-2311 | 小猪存钱罐给的钱与VIP等级无关，所以GameSetting中IAPCatalog页中的ID=8~11的内购，AffectByVipLevel列应该为0。目前的现状是不管AffectByVipLevel列是否为0，小猪存钱罐的钱都与VP等级无关 | Bug | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 28/Nov/17 3:34 PM |  | 28/Nov/17 3:34 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9320
TrojanHorse | TROJ-2354 | Dice重验证发补偿后，应该加弹窗逻辑明确告诉玩家补偿了啥 | Task | To Do | Major | Unresolved | fanrongqi | liuwen | liuwen | 29/Nov/17 8:57 PM |  | 29/Nov/17 8:57 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9361
TrojanHorse | TROJ-2372 | Trojan_StartPurchase、Trojan_ChannelSuccessPurchase、Trojan_SuccessVerify事件的str8和str5重复了，删去str8中的内容 | Task | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 30/Nov/17 1:52 PM |  | 30/Nov/17 1:52 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9380
TrojanHorse | TROJ-2403 | 统一所有弹窗的动画，程序自动配置 | Task | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 01/Dec/17 12:46 PM |  | 01/Dec/17 12:46 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9423
TrojanHorse | TROJ-2361 | iPad适配-新手礼包放大至110% | Task | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 29/Nov/17 9:28 PM |  | 01/Dec/17 1:47 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9368
TrojanHorse | TROJ-2458 | 再打一个上周最终报的tag，在此tag基础上，添加逻辑：时间调整为12月21日。 | Task | In Review | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 04/Dec/17 11:12 AM |  | 05/Dec/17 11:28 AM |  |  | 1.20.1 |  |  | 0 | 1 | [8 empty] | 目的是第二次测试圣诞节的内容。 | [7 empty] | None | [8 empty] | 9479
TrojanHorse | TROJ-2404 | VIP机台卷轴及切图-V3 钻石机台，jackpot玩法 | Task | To Do | Major | Unresolved | lihuichao | 于笑晖 | xuchengkai | 01/Dec/17 12:51 PM |  | 01/Dec/17 2:32 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9424
TrojanHorse | TROJ-2405 | VIP机台背景及切图-V3 钻石机台 | Task | To Do | Major | Unresolved | lihuichao | 于笑晖 | xuchengkai | 01/Dec/17 12:51 PM |  | 01/Dec/17 2:31 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9425
TrojanHorse | TROJ-2389 | VIP机台元素背景及他们的切图-V3 钻石机台 | Task | To Do | Major | Unresolved | lihuichao | 于笑晖 | 于笑晖 | 01/Dec/17 11:56 AM |  | 04/Dec/17 11:39 AM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9411
TrojanHorse | TROJ-2472 | 彩虹主题看久了卷轴显得有点脏。要提高卷轴的亮度 | Task | To Do | Major | Unresolved | lihuichao | xuchengkai | xuchengkai | 04/Dec/17 11:52 AM |  | 04/Dec/17 11:52 AM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9493
TrojanHorse | TROJ-2392 | VIP机台大厅系统标志物 | Task | To Do | Major | Unresolved | lihuichao | 于笑晖 | 于笑晖 | 01/Dec/17 11:58 AM |  | 04/Dec/17 5:42 PM |  |  | 1.20.1 |  |  | 0 | 1 | [8 empty] | 4.玩家喜爱的机台的标记物 5.VIP机台标志物（两种） | [7 empty] | None | [8 empty] | 9414
TrojanHorse | TROJ-2435 | VIP升级全服提示的文本框 | Task | To Do | Major | Unresolved | lihuichao | 于笑晖 | 于笑晖 | 01/Dec/17 2:21 PM |  | 04/Dec/17 5:42 PM |  |  | 1.20.1 |  |  | 0 | 1 | _thumb_13213.png | [15 empty] | None | [8 empty] | 9453
TrojanHorse | TROJ-2011 | 付费玩家监控 | Task | To Do | Major | Unresolved | linli | xuchengkai | xuchengkai | 08/Nov/17 11:09 AM |  | 04/Dec/17 2:33 PM |  |  | 1.20.1 |  |  | 0 | 2 | [16 empty] | None | [8 empty] | 8946
TrojanHorse | TROJ-1916 | 整理所有UI图片的Tag，原则上一个UI下的所有图用一个Tag | Task | To Do | Major | Unresolved | liuwen | liuwen | liuwen | 03/Nov/17 12:09 PM | 05/Dec/17 3:32 PM | 27/Nov/17 9:49 AM |  |  | 1.20.1 |  |  | 0 | 1 | [8 empty] | 目前图片的Tag管理太乱了，需要整体过一遍 | [7 empty] | None | [8 empty] | 8809
TrojanHorse | TROJ-2431 | 验收其他程序的工作 | Task | To Do | Major | Unresolved | liuwen | xuchengkai | xuchengkai | 01/Dec/17 2:13 PM |  | 01/Dec/17 2:13 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9449
TrojanHorse | TROJ-2132 | 优化机台场景的所有性能，包括draw call，写文件，内存，texture等 | Task | To Do | Major | Unresolved | liuwen | liuwen | liuwen | 16/Nov/17 6:22 PM |  | 01/Dec/17 2:51 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9117
TrojanHorse | TROJ-2380 | 重复写UserData文件操作太多，需要代码都过一遍优化 | Task | To Do | Major | Unresolved | liuwen | liuwen | liuwen | 30/Nov/17 6:59 PM |  | 01/Dec/17 2:46 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9397
TrojanHorse | TROJ-2476 | 和美术一起整理机台的层级关系，增加特效层 | Task | To Do | Major | Unresolved | liuwen | liuwen | liuwen | 04/Dec/17 1:47 PM |  | 04/Dec/17 1:47 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9497
TrojanHorse | TROJ-2223 | 弹出进度选择框后，如果玩家选择等级低的进度，就弹出警告弹窗。 | Task | To Do | Major | Unresolved | liuwen | xuchengkai | xuchengkai | 20/Nov/17 4:49 PM |  | 04/Dec/17 3:35 PM |  |  | 1.20.1 |  |  | 0 | 1 | [8 empty] | 弹窗内容 正文：Do you wanna give up the higher level progress? 左按钮：Yes，右按钮：No 玩家选Yes，加载低等级进度。 玩家选No，关掉警告弹窗，玩家重新选择进度。 | [7 empty] | None | [8 empty] | 9224
TrojanHorse | TROJ-2378 | 付费打点bug | Bug | In Review | Major | Unresolved | liuwen | Zhao Yunlong | Zhao Yunlong | 30/Nov/17 6:13 PM | 05/Dec/17 3:43 PM | 04/Dec/17 6:45 PM |  |  | 1.20.1 |  |  | 0 | 1 | _thumb_13209.png | [7 empty] | start里面还是记录的9.99给40000 credits，但是由于玩家在购买过程中升级成了vip1，在success里面就显示给了44000 credits。而且此时有付费双倍credits的活动，玩家实际得到了80000credits。这里应该显示玩家实际得到的credits。 | [7 empty] | None | [8 empty] | 9395
TrojanHorse | TROJ-2441 | ios，安卓，大R分表需求 | Task | To Do | Major | Unresolved | liuwen | Zhao Yunlong | Zhao Yunlong | 01/Dec/17 2:33 PM |  | 05/Dec/17 3:35 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9459
TrojanHorse | TROJ-2271 | 破解5卷轴机器的逻辑和数值 | Task | To Do | Major | Unresolved | liuwen | xuchengkai | xuchengkai | 24/Nov/17 2:01 PM | 05/Dec/17 3:42 PM | 05/Dec/17 3:42 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9276
TrojanHorse | TROJ-2385 | 卷轴框和计钱框的Bar之间要有特效的层级。（为了解决M18功夫主题机器的特效层级问题） | Task | To Do | Major | Unresolved | liuwen | xuchengkai | xuchengkai | 01/Dec/17 11:41 AM | 05/Dec/17 3:44 PM | 05/Dec/17 3:44 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9406
TrojanHorse | TROJ-2427 | App Store商店视频，竖版，先做一个尺寸 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 01/Dec/17 1:59 PM |  | 04/Dec/17 11:40 AM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9445
TrojanHorse | TROJ-2467 | 所有购买弹窗后面添加环境光效，渲染赌场气氛。可以借鉴viva slots一样 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 04/Dec/17 11:42 AM |  | 04/Dec/17 11:51 AM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9488
TrojanHorse | TROJ-1165 | M14蝴蝶与卷轴不是很搭 | Story | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 27/Jul/17 9:07 PM | 05/Dec/17 3:03 PM | 01/Dec/17 12:33 PM |  |  | 1.20.1 |  |  | 0 | 1 | [8 empty] | 做完之后，直接替换 | [7 empty] | None | [8 empty] | 7700
TrojanHorse | TROJ-2397 | 新机器大厅公告牌及切图-水晶鞋主题 | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 01/Dec/17 12:32 PM |  | 01/Dec/17 12:32 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9418
TrojanHorse | TROJ-2434 | VIP Room幕布 | Task | To Do | Major | Unresolved | wangyaohan | 于笑晖 | 于笑晖 | 01/Dec/17 2:21 PM |  | 01/Dec/17 2:21 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9452
TrojanHorse | TROJ-1613 | 哥伦布机台UI改进初步设想 | Task | In Review | Major | Unresolved | wangyaohan | 于笑晖 | Yi Zhu | 30/Sep/17 7:50 AM |  | 05/Dec/17 2:24 PM |  | 1.15.0 | 1.20.1 |  |  | 0 | 1 | [8 empty] | 现在的卷轴框还是矩形的，是不是可以做成真正的船的驾驶室的挡风玻璃样式，这样就更像在开船？似乎不用拘泥矩形。这版本不用调整 | [7 empty] | None | [8 empty] | 8315
TrojanHorse | TROJ-2335 | 新机器大厅公告牌及切图-忍者主题 | Task | In Review | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 29/Nov/17 3:24 PM | 05/Dec/17 3:04 PM | 05/Dec/17 2:24 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9343
TrojanHorse | TROJ-2400 | 新机器拼卷轴UI-水晶鞋主题 | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 01/Dec/17 12:38 PM | 05/Dec/17 3:05 PM | 05/Dec/17 2:25 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9420
TrojanHorse | TROJ-2396 | 新机器拼背景UI-水晶鞋主题 | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 01/Dec/17 12:31 PM |  | 05/Dec/17 2:25 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9417
TrojanHorse | TROJ-2489 | 圣诞节FB Post图-200% Sale+圣诞节机器 | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 05/Dec/17 2:28 PM |  | 05/Dec/17 2:28 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9516
TrojanHorse | TROJ-2490 | 圣诞节FB Post图-200% Sale+新年 | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 05/Dec/17 2:29 PM |  | 05/Dec/17 2:29 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9517
TrojanHorse | TROJ-2488 | 周六FB Post图 | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 05/Dec/17 2:26 PM |  | 05/Dec/17 2:26 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9515
TrojanHorse | TROJ-2493 | 圣诞节FB Post图-双倍每小时奖励 | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 05/Dec/17 2:30 PM |  | 05/Dec/17 2:30 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9520
TrojanHorse | TROJ-2492 | 圣诞节FB Post图-双倍max win | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 05/Dec/17 2:30 PM |  | 05/Dec/17 2:30 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9519
TrojanHorse | TROJ-2491 | 圣诞节FB Post图-Giveaway time | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 05/Dec/17 2:29 PM |  | 05/Dec/17 2:29 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9518
TrojanHorse | TROJ-2278 | 邮件营销，给神豪发图片式邮件的需求 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 24/Nov/17 4:21 PM | 05/Dec/17 3:05 PM | 29/Nov/17 9:47 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9281
TrojanHorse | TROJ-2425 | Dice重验证发补偿后，明确告诉玩家补偿了啥的弹窗UI的需求 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 01/Dec/17 1:49 PM |  | 01/Dec/17 1:49 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9443
TrojanHorse | TROJ-2430 | 跟踪HWS经济系统，在神策上建立监控 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 01/Dec/17 2:01 PM |  | 01/Dec/17 2:01 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9448
TrojanHorse | TROJ-2426 | App Store商店视频，竖版需求 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 01/Dec/17 1:59 PM | 05/Dec/17 3:05 PM | 01/Dec/17 1:59 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9444
TrojanHorse | TROJ-2437 | 在配置表中替换新机器大厅公告牌-增加水晶鞋，换下彩虹和淘金热 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 01/Dec/17 2:29 PM |  | 01/Dec/17 2:29 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9455
TrojanHorse | TROJ-2446 | 给怡澄各个活动的列表，包含各种条件。方便测试 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 01/Dec/17 4:35 PM |  | 01/Dec/17 4:35 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9464
TrojanHorse | TROJ-2463 | Jackpot机制修改，用时间差来代替实时计算奖金池的需求 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 04/Dec/17 11:35 AM | 05/Dec/17 3:41 PM | 04/Dec/17 11:35 AM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9484
TrojanHorse | TROJ-2447 | 1.18.1玩家反馈连不上FB | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 01/Dec/17 4:57 PM |  | 04/Dec/17 12:00 PM |  |  | 1.20.1 |  |  | 0 | 1 | [8 empty] | 等待玩家回信 | [7 empty] | None | [8 empty] | 9466
TrojanHorse | TROJ-2481 | 收集机台是否需要关闭看广告的双倍win的机制 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 04/Dec/17 6:11 PM |  | 04/Dec/17 6:11 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9506
TrojanHorse | TROJ-2452 | 召回大R | Task | To Do | Critical | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 04/Dec/17 9:32 AM |  | 05/Dec/17 2:23 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9472
TrojanHorse | TROJ-1116 | 根据好友人数，增加每日奖励（调整UI、动画、逻辑） | Story | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 19/Jul/17 8:11 PM |  | 17/Nov/17 3:46 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 7538
TrojanHorse | TROJ-2367 | 剩余机台reel表检查 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 30/Nov/17 11:13 AM |  | 30/Nov/17 11:13 AM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9375
TrojanHorse | TROJ-2375 | 用户分群活动，推送细化 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 30/Nov/17 4:24 PM |  | 30/Nov/17 4:24 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9390
TrojanHorse | TROJ-2455 | 用户分群量化分析 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 04/Dec/17 9:45 AM |  | 04/Dec/17 9:45 AM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9475
TrojanHorse | TROJ-2475 | 篮球机器玩法描述看不懂 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 04/Dec/17 1:38 PM |  | 04/Dec/17 1:38 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9496
TrojanHorse | TROJ-2357 | iPad适配-jackpot中奖后小机器提示信息应该放大并上移 | Bug | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 29/Nov/17 9:17 PM | 05/Dec/17 3:44 PM | 29/Nov/17 9:40 PM |  |  | 1.20.1 |  |  | 0 | 1 | _thumb_13202.png | [15 empty] | None | [8 empty] | 9364
TrojanHorse | TROJ-1377 | 点击好友发的FB request，进入游戏后没有直接跳转相关界面（比如送礼物或收礼物） | Bug | To Do | Major | Unresolved | zhousen | Yi Zhu | Yi Zhu | 22/Aug/17 6:46 PM |  | 30/Nov/17 10:05 PM |  | iOS1.3.0+GP1.9.0 | 1.20.1 |  |  | 0 | 2 | _thumb_13069.png | [15 empty] | None | [8 empty] | 7930
TrojanHorse | TROJ-2281 | M6水晶鞋机器的替换资源和效果和逻辑 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 24/Nov/17 6:22 PM |  | 30/Nov/17 10:05 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9284
TrojanHorse | TROJ-2356 | 彩虹主题机器的遮罩有问题 | Bug | In Review | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 29/Nov/17 9:10 PM |  | 04/Dec/17 11:52 AM |  |  | 1.20.1 |  |  | 0 | 2 | _thumb_13201.png | [15 empty] | None | [8 empty] | 9363
TrojanHorse | TROJ-2243 | iPad适配-M15小猪转盘的背景切线露出来了，见附件图 | Task | In Review | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 23/Nov/17 3:30 PM | 05/Dec/17 3:43 PM | 04/Dec/17 1:49 PM |  |  | 1.20.1 |  |  | 0 | 2 | _thumb_13174.png | [15 empty] | None | [8 empty] | 9248
TrojanHorse | TROJ-2379 | Trojan_Spin事件中的str6表示小游戏属性，有些机器的设置错误，详情看附件 | Bug | In Review | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 30/Nov/17 6:19 PM |  | 04/Dec/17 2:07 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9396
TrojanHorse | TROJ-2353 | iPad适配-锦标赛获奖界面左边遮罩缺1-2个像素，右边缺3-4个像素 | Bug | In Review | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 29/Nov/17 8:41 PM |  | 04/Dec/17 2:16 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9360
TrojanHorse | TROJ-2257 | 玩家Feedback中添加PayAmount字段 | Task | In Review | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 23/Nov/17 8:44 PM |  | 04/Dec/17 2:50 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9262
TrojanHorse | TROJ-2478 | 彩虹机器，转盘完成后，结算过程中，出现一条黑色线 | Bug | In Review | Major | Unresolved | zhousen | 沈怡澄 | 沈怡澄 | 04/Dec/17 3:42 PM |  | 05/Dec/17 11:23 AM |  |  | 1.20.1 |  | 04/Dec/17 | 0 | 2 | _thumb_13300.png | [15 empty] | None | [8 empty] | 9500
TrojanHorse | TROJ-1998 | 线上版本HOME OUT之后HOME In卡死 | Bug | To Do | Minor | Unresolved | zhousen | 于笑晖 | 于笑晖 | 06/Nov/17 5:59 PM |  | 01/Dec/17 1:45 PM |  |  | 1.20.1 |  |  | 0 | 1 | [8 empty] | 没有crash和闪退；界面不动。Home out之前在下载机台，home out之后打了个电话不知道会不会影响。 | [7 empty] | None | [8 empty] | 8923
TrojanHorse | TROJ-2197 | M39-多线Jackpot机台 美术需求及跟进 | Bug | To Do | Major | Unresolved | 于笑晖 | 于笑晖 | 于笑晖 | 17/Nov/17 4:19 PM |  | 29/Nov/17 8:54 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9189
TrojanHorse | TROJ-2207 | 研究五卷轴机器的数值 | Task | In Review | Major | Unresolved | 于笑晖 | xuchengkai | xuchengkai | 20/Nov/17 9:37 AM |  | 01/Dec/17 2:29 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9208
TrojanHorse | TROJ-2438 | M19忍者机台的跟进 | Task | To Do | Major | Unresolved | 于笑晖 | 于笑晖 | 于笑晖 | 01/Dec/17 2:30 PM |  | 01/Dec/17 2:30 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9456
TrojanHorse | TROJ-2440 | M39 Lucky Jackpot机台的Paytable | Task | To Do | Major | Unresolved | 于笑晖 | 于笑晖 | 于笑晖 | 01/Dec/17 2:31 PM | 05/Dec/17 3:28 PM | 01/Dec/17 2:31 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9458
TrojanHorse | TROJ-2439 | M19忍者机台Paytable | Task | To Do | Major | Unresolved | 于笑晖 | 于笑晖 | 于笑晖 | 01/Dec/17 2:30 PM |  | 01/Dec/17 2:30 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9457
TrojanHorse | TROJ-2448 | 给QA准备一张大字报 | Task | To Do | Major | Unresolved | 于笑晖 | 于笑晖 | 于笑晖 | 01/Dec/17 5:00 PM | 05/Dec/17 3:28 PM | 01/Dec/17 5:00 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9467
TrojanHorse | TROJ-1798 | Big Win, Epic Win整体视觉效果优化。缩小BigWin、EpicWin的文字 | Task | To Do | Critical | Unresolved | 徐盛富 | Yi Zhu | Yi Zhu | 27/Oct/17 3:09 PM | 05/Dec/17 3:44 PM | 20/Nov/17 2:47 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 8665
TrojanHorse | TROJ-2391 | VIP机台-新的Paytable界面（可能） | Task | To Do | Major | Unresolved | 徐盛富 | 于笑晖 | 于笑晖 | 01/Dec/17 11:57 AM |  | 01/Dec/17 1:02 PM |  |  | 1.20.1 |  |  | 0 | 1 | [7 empty] | 最大奖与Bet值有关，会显示两种最大奖倍数 | [8 empty] | None | [8 empty] | 9413
TrojanHorse | TROJ-2410 | VIP机台-Bet框和Win框等的修改（提升最高Bet值） | Task | To Do | Major | Unresolved | 徐盛富 | 于笑晖 | xuchengkai | 01/Dec/17 12:59 PM |  | 01/Dec/17 1:01 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9429
TrojanHorse | TROJ-2421 | 美术程序配合缩图 | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 01/Dec/17 1:41 PM |  | 01/Dec/17 1:41 PM |  |  | 1.20.1 |  |  | 0 | 1 | [8 empty] | 1 主要是过一遍所有的大图，把很多图用更小的尺寸去做 下列图可以考虑： Fb_Tex Fb_Tex02 Images/Dice/bg.jpg Images/PayTable/BG.png mianban and mianban0 两个一样的图SpecialOffer_Icon02 2 开会教美术如何用省资源的方式作图 | [7 empty] | None | [8 empty] | 9439
TrojanHorse | TROJ-2422 | 弹出进度选择框后，如果玩家选择等级低的进度，就弹出警告弹窗的UI | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 01/Dec/17 1:43 PM |  | 01/Dec/17 1:43 PM |  |  | 1.20.1 |  |  | 0 | 1 | [8 empty] | 弹窗内容 正文：Do you wanna give up the higher level progress? 左按钮：Yes，右按钮：No 玩家选Yes，加载低等级进度。 玩家选No，关掉警告弹窗，玩家重新选择进度。 | [7 empty] | None | [8 empty] | 9440
TrojanHorse | TROJ-2424 | Dice重验证发补偿后，明确告诉玩家补偿了啥的弹窗UI | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 01/Dec/17 1:48 PM |  | 01/Dec/17 1:48 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9442
TrojanHorse | TROJ-2445 | 放大EpicWin和BigWin的Collect按钮 | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 01/Dec/17 4:03 PM |  | 01/Dec/17 4:03 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9463
TrojanHorse | TROJ-2450 | 大厅大机器解锁的牌子与卷轴位置没对齐 | Bug | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 01/Dec/17 8:20 PM | 05/Dec/17 3:33 PM | 01/Dec/17 8:20 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9470
TrojanHorse | TROJ-2401 | 等耀汉哥伦布机器UI修改好之后，修改动画特效 | Task | To Do | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 01/Dec/17 12:41 PM |  | 01/Dec/17 12:41 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9421
TrojanHorse | TROJ-2418 | 新机器小游戏特效-M6水晶鞋主题，Freespin时背景特效 | Task | To Do | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 01/Dec/17 1:36 PM |  | 01/Dec/17 1:36 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9436
TrojanHorse | TROJ-1939 | 新机器卷轴特效-M6水晶鞋主题 | Task | To Do | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 03/Nov/17 1:13 PM |  | 01/Dec/17 1:36 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 8831
TrojanHorse | TROJ-2456 | M24中国主题背景加金片 | Task | To Do | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 04/Dec/17 9:57 AM |  | 04/Dec/17 9:58 AM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9476
TrojanHorse | TROJ-2444 | M1wild特效到EpicWin遮罩前面了 | Task | In Review | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 01/Dec/17 4:01 PM |  | 04/Dec/17 3:49 PM |  |  | 1.20.1 |  |  | 0 | 1 | _thumb_13214.png | [15 empty] | None | [8 empty] | 9462
TrojanHorse | TROJ-2409 | 新机器小游戏UI及切图-聚宝盆主题，Freespin | Task | To Do | Major | Unresolved | 肖樊 | xuchengkai | xuchengkai | 01/Dec/17 12:58 PM |  | 05/Dec/17 2:41 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9428
TrojanHorse | TROJ-2155 | 新机器卷轴及切图-聚宝盆主题 | Task | To Do | Major | Unresolved | 肖樊 | xuchengkai | xuchengkai | 16/Nov/17 10:59 PM |  | 05/Dec/17 2:41 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9138
TrojanHorse | TROJ-2407 | 新机器元素背景及他们的切图-聚宝盆主题 | Task | To Do | Major | Unresolved | 肖樊 | xuchengkai | xuchengkai | 01/Dec/17 12:55 PM |  | 05/Dec/17 2:42 PM |  |  | 1.20.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9427