## Sheet1
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Sprint | Epic Link | Epic Name | Epic Status | Epic Color | Flagged | Epic/Theme | Story Points | Business Value | Rank
TrojanHorse | TROJ-2566 | 停在大厅机台，第二天就不出daily bonus | Bug | To Do | Critical | Unresolved | fanrongqi | Zhao Yunlong | Zhao Yunlong | 15/Dec/17 10:46 AM | 18/Dec/17 9:55 AM | 15/Dec/17 10:46 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9640
TrojanHorse | TROJ-2311 | 小猪存钱罐给的钱与VIP等级无关，所以GameSetting中IAPCatalog页中的ID=8~11的内购，AffectByVipLevel列应该为0。目前的现状是不管AffectByVipLevel列是否为0，小猪存钱罐的钱都与VP等级无关 | Bug | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 28/Nov/17 3:34 PM |  | 11/Dec/17 10:25 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9319
TrojanHorse | TROJ-2293 | 盛富的手机显示大机台大厅背景有一条缝。（之前好像是说只有我的手机有） | Task | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 27/Nov/17 9:34 AM |  | 11/Dec/17 10:26 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9296
TrojanHorse | TROJ-2203 | 统一debug版和release版的每小时奖励，冷却时间都是1小时 | Task | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 17/Nov/17 7:50 PM |  | 11/Dec/17 10:25 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9202
TrojanHorse | TROJ-1348 | Fabric ：关于推送的Crash | Bug | To Do | Major | Unresolved | liuwen | xuchengkai | xuchengkai | 18/Aug/17 2:49 PM |  | 13/Dec/17 9:13 PM |  |  | 1.21.2 |  |  | 0 | 3 | [8 empty] | UnityNotificationManager.java line 133 /react-text net.agasper.unitynotification.UnityNotificationManager.onReceive 最近七天（至20170817），1.9.0版本有8个崩溃 https://fabric.io/citrusjoy/android/apps/com.citrusjoy.trojan/issues/5945dd0dbe077a4dcc46610e?time=last-seven-days | [7 empty] | None | [8 empty] | 7901
TrojanHorse | TROJ-1241 | 建立自动测试机制自动跑所有机台RTP，放到jenkins上，当出现较大偏差时报错 | Story | To Do | Major | Unresolved | liuwen | xuchengkai | xuchengkai | 08/Aug/17 1:23 PM |  | 13/Dec/17 9:11 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 7799
TrojanHorse | TROJ-1972 | home out时，能收到远程推送，但是不会打点，firebase也不会统计 | Bug | To Do | Major | Unresolved | liuwen | xuchengkai | xuchengkai | 03/Nov/17 10:00 PM |  | 13/Dec/17 9:13 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 8891
TrojanHorse | TROJ-2518 | 进入游戏后，loading界面出现跳一下的过程 | Bug | To Do | Major | Unresolved | liuwen | 沈怡澄 | 沈怡澄 | 08/Dec/17 11:14 AM |  | 13/Dec/17 9:13 PM |  |  | 1.21.2 |  | 08/Dec/17 | 0 | 1 | [16 empty] | None | [8 empty] | 9551
TrojanHorse | TROJ-2270 | 代码数值加密后续（包体、内存） | Task | To Do | Major | Unresolved | liuwen | xuchengkai | xuchengkai | 24/Nov/17 2:00 PM |  | 13/Dec/17 9:11 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9274
TrojanHorse | TROJ-2570 | IOS Debug包240 进出M16时崩溃 | Bug | To Do | Major | Unresolved | liuwen | 于笑晖 | 于笑晖 | 15/Dec/17 11:40 AM | 18/Dec/17 8:43 AM | 15/Dec/17 11:40 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9646
TrojanHorse | TROJ-2324 | 社区视频-M19忍者主题 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 29/Nov/17 3:04 PM |  | 11/Dec/17 10:08 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9332
TrojanHorse | TROJ-2325 | 社区视频-聚宝盆主题 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 29/Nov/17 3:08 PM |  | 11/Dec/17 10:09 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9333
TrojanHorse | TROJ-2571 | 新游戏名称，关键词确定 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 15/Dec/17 11:41 AM |  | 15/Dec/17 11:41 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9647
TrojanHorse | TROJ-1377 | 点击好友发的FB request，进入游戏后没有直接跳转相关界面（比如送礼物或收礼物） | Task | To Do | Major | Unresolved | zhousen | Yi Zhu | Yi Zhu | 22/Aug/17 6:46 PM |  | 15/Dec/17 3:11 PM |  | iOS1.3.0+GP1.9.0 | 1.21.2 |  |  | 0 | 2 | _thumb_13069.png | [15 empty] | None | [8 empty] | 7930
TrojanHorse | TROJ-2552 | 水晶鞋机器，看视频按钮的层级有小错误 | Bug | To Do | Major | Unresolved | zhousen | 沈怡澄 | 沈怡澄 | 12/Dec/17 2:43 PM | 18/Dec/17 8:47 AM | 15/Dec/17 3:11 PM |  |  | 1.21.2 |  | 12/Dec/17 | 0 | 1 | _thumb_13326.png | [15 empty] | None | [8 empty] | 9606
TrojanHorse | TROJ-1998 | 线上版本HOME OUT之后HOME In卡死 | Bug | To Do | Minor | Unresolved | zhousen | 于笑晖 | 于笑晖 | 06/Nov/17 5:59 PM |  | 15/Dec/17 10:15 AM |  |  | 1.21.2 |  |  | 0 | 1 | [8 empty] | 没有crash和闪退；界面不动。Home out之前在下载机台，home out之后打了个电话不知道会不会影响。 | [7 empty] | None | [8 empty] | 8923
TrojanHorse | TROJ-2197 | M39-多线Jackpot机台 美术需求及跟进 | Bug | To Do | Major | Unresolved | 于笑晖 | 于笑晖 | 于笑晖 | 17/Nov/17 4:19 PM |  | 15/Dec/17 2:07 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9188
TrojanHorse | TROJ-2394 | VIP系统的跟进 | Task | To Do | Major | Unresolved | 于笑晖 | 于笑晖 | 于笑晖 | 01/Dec/17 12:01 PM |  | 15/Dec/17 2:07 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9414
TrojanHorse | TROJ-2342 | 新机器特效调优（周五讨论之后）-聚宝盆主题 | Task | To Do | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 29/Nov/17 4:17 PM |  | 01/Dec/17 1:34 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9349
TrojanHorse | TROJ-2341 | 新机器特效调优（周五讨论之后）-忍者主题 | Task | To Do | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 29/Nov/17 4:17 PM |  | 01/Dec/17 1:35 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9348