## Sheet1
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Sprint | Epic Link | Epic Name | Epic Status | Epic Color | Flagged | Epic/Theme | Story Points | Business Value | Rank
TrojanHorse | TROJ-2688 | VIP机台元素动画-V1 | Task | To Do | Major | Unresolved | dongtao | xuchengkai | xuchengkai | 22/Dec/17 5:44 PM |  | 22/Dec/17 5:44 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9793
TrojanHorse | TROJ-2691 | 换皮包-每小时奖励转盘的动画，沿用Huge Win Slots旋转节奏 | Task | To Do | Major | Unresolved | dongtao | xuchengkai | xuchengkai | 22/Dec/17 5:45 PM |  | 22/Dec/17 5:45 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9796
TrojanHorse | TROJ-2689 | VIP机台元素动画-V2 | Task | To Do | Major | Unresolved | dongtao | xuchengkai | xuchengkai | 22/Dec/17 5:44 PM |  | 22/Dec/17 5:44 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9794
TrojanHorse | TROJ-2754 | 天使与魔鬼动画，天使的动画像卡顿了一样 | Bug | To Do | Major | Unresolved | dongtao | 沈怡澄 | 沈怡澄 | 26/Dec/17 3:05 PM |  | 26/Dec/17 3:46 PM |  |  | 1.21.2 |  | 26/Dec/17 | 0 | 1 | [16 empty] | None | [8 empty] | 9868
TrojanHorse | TROJ-2690 | VIP机台元素动画-V3 | Task | To Do | Major | Unresolved | dongtao | xuchengkai | xuchengkai | 22/Dec/17 5:44 PM |  | 28/Dec/17 6:34 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9795
TrojanHorse | TROJ-2700 | 换皮包-大厅BGM | Task | To Do | Major | Unresolved | FangLei | xuchengkai | xuchengkai | 22/Dec/17 5:48 PM |  | 22/Dec/17 5:48 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9805
TrojanHorse | TROJ-2566 | 停在大厅机台，第二天就不出daily bonus | Bug | In Progress | Critical | Unresolved | fanrongqi | Zhao Yunlong | Zhao Yunlong | 15/Dec/17 10:46 AM | 02/Jan/18 9:41 AM | 29/Dec/17 6:40 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9639
TrojanHorse | TROJ-2582 | 小猪存钱罐小猪跑到折扣标签上了 | Bug | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 18/Dec/17 11:33 AM | 29/Dec/17 1:50 PM | 18/Dec/17 11:33 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9666
TrojanHorse | TROJ-2387 | VIP系统 | New Feature | In Progress | Major | Unresolved | fanrongqi | 于笑晖 | 于笑晖 | 01/Dec/17 11:48 AM |  | 25/Dec/17 9:43 AM |  |  | 1.21.2 |  |  | 0 | 1 | [8 empty] | 1.在MachineUnlockSetting中增加一列，配置机台解锁所需的VIP等级 2.将VIP机台标志物放置到相应位置 3.玩家将机台标记为喜爱机台时，将机台自动放置到最前面的位置(小机台的最前面或者大机台的最前面） 4.玩家解锁新的VIP机台时，弹出提示框，并且支持点击提示框自动移动到相应机台的位置 5.解锁新的机台时，移动过去之后再播放解锁动画 6.玩家高Bet值时，中奖率降低（与付费玩家保护机制做法类似） 7.玩家在大厅向左拖动时，播放幕布动画并且进入VIPROOM（幕布与小机台不同，且考虑到VIProom可能同时有大小机台，背景需要重新设计，整个流程需要有豪华的感觉） 8.VIP升级全服通告，若玩家在线十分钟（可配置）都没有人升级，则播放机器人升级的通告（1-8级随机） 9.Ratio随Bet变化（可能） 第九条可以考虑是否做 | [7 empty] | None | [8 empty] | 9408
TrojanHorse | TROJ-2203 | 统一debug版和release版的每小时奖励，冷却时间都是1小时 | Task | In Review | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 17/Nov/17 7:50 PM |  | 25/Dec/17 10:16 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9202
TrojanHorse | TROJ-2563 | adjust需要回传神策的distinct_id，以便后期做数据分析 | Story | In Review | Major | Unresolved | fanrongqi | linli | linli | 14/Dec/17 5:07 PM |  | 27/Dec/17 11:08 AM |  |  | 1.21.2 |  |  | 0 | 1 | [8 empty] | adjust需要回传神策的distinct_id，以便后期做数据分析 | [7 empty] | None | [8 empty] | 9627
TrojanHorse | TROJ-2746 | 从卷轴界面回到大厅之后，出现每小时奖励，但是被幕布遮住，幕布也不自动缩回 | Bug | In Progress | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 25/Dec/17 2:52 PM |  | 27/Dec/17 9:07 PM |  |  | 1.21.2 |  |  | 0 | 2 | [8 empty] | 大厅幕布的层级应该在每日奖励之后 | [7 empty] | None | [8 empty] | 9856
TrojanHorse | TROJ-2763 | 神策打点-userprofile中添加字段country | Task | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 29/Dec/17 11:37 AM | 29/Dec/17 1:51 PM | 29/Dec/17 11:37 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9884
TrojanHorse | TROJ-2293 | 盛富的手机显示大机台大厅背景有一条缝。（之前好像是说只有我的手机有） | Task | In Review | Major | Unresolved | fanrongqi | 徐盛富 | xuchengkai | 27/Nov/17 9:34 AM |  | 29/Dec/17 12:26 PM |  |  | 1.21.2 |  |  | 0 | 2 | [16 empty] | None | [8 empty] | 9296
TrojanHorse | TROJ-2767 | 进入VIP机器界面，返回大厅，进普通机器，手机物理返回键点击无效 | Bug | To Do | Major | Unresolved | fanrongqi | 沈怡澄 | 沈怡澄 | 29/Dec/17 11:55 AM |  | 29/Dec/17 1:06 PM |  |  | 1.21.2 |  | 29/Dec/17 | 0 | 1 | [16 empty] | None | [8 empty] | 9888
TrojanHorse | TROJ-2765 | 小机器进入VIP机器后，在返回普通机器，幕布错误 | Bug | To Do | Major | Unresolved | fanrongqi | 沈怡澄 | 沈怡澄 | 29/Dec/17 11:50 AM |  | 29/Dec/17 1:06 PM |  |  | 1.21.2 |  | 29/Dec/17 | 0 | 1 | [16 empty] | None | [8 empty] | 9886
TrojanHorse | TROJ-2764 | 解锁VIP机器后，普通机器解锁出现问题 | Bug | To Do | Major | Unresolved | fanrongqi | 沈怡澄 | 沈怡澄 | 29/Dec/17 11:49 AM |  | 29/Dec/17 1:06 PM |  |  | 1.21.2 |  | 29/Dec/17 | 0 | 1 | [16 empty] | None | [8 empty] | 9885
TrojanHorse | TROJ-2774 | VIP房间-vip升级公告 | Task | To Do | Major | Unresolved | fanrongqi | xuchengkai | xuchengkai | 29/Dec/17 1:52 PM | 29/Dec/17 1:52 PM | 29/Dec/17 1:52 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9895
TrojanHorse | TROJ-2766 | VIP机器按钮可以进行多次点击 | Bug | In Review | Major | Unresolved | fanrongqi | 沈怡澄 | 沈怡澄 | 29/Dec/17 11:50 AM |  | 29/Dec/17 6:41 PM |  |  | 1.21.2 |  | 29/Dec/17 | 0 | 1 | [16 empty] | None | [8 empty] | 9887
TrojanHorse | TROJ-2363 | 锦标赛结算时退出机台，会卡死 | Bug | To Do | Minor | Unresolved | fanrongqi | 于笑晖 | 于笑晖 | 29/Nov/17 10:26 PM | 29/Dec/17 1:51 PM | 27/Dec/17 11:16 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9369
TrojanHorse | TROJ-2643 | 换皮包-五卷轴机器，1周做好给程序特效，1周来切图适配调整 | Task | To Do | Major | Unresolved | lihuichao | xuchengkai | xuchengkai | 22/Dec/17 4:59 PM | 29/Dec/17 1:55 PM | 22/Dec/17 4:59 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9749
TrojanHorse | TROJ-2652 | 换皮包-每日奖励，固定奖励 | Task | To Do | Major | Unresolved | lihuichao | xuchengkai | xuchengkai | 22/Dec/17 5:10 PM | 02/Jan/18 9:43 AM | 22/Dec/17 5:10 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9758
TrojanHorse | TROJ-2748 | 把彩虹机器的卷轴背景做的简单些，不要那层暗色 | Task | To Do | Major | Unresolved | lihuichao | xuchengkai | xuchengkai | 25/Dec/17 4:45 PM |  | 25/Dec/17 4:45 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9861
TrojanHorse | TROJ-2644 | 换皮包-每小时奖励转盘 | Task | To Do | Major | Unresolved | lihuichao | xuchengkai | xuchengkai | 22/Dec/17 5:00 PM |  | 28/Dec/17 6:33 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9750
TrojanHorse | TROJ-2619 | PM系统增加发送信息的记录，方便我们查阅 | Task | In Review | Major | Unresolved | linli | Zhao Yunlong | xuchengkai | 21/Dec/17 6:48 PM |  | 26/Dec/17 1:58 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9722
TrojanHorse | TROJ-2011 | 付费玩家监控 | Task | To Do | Major | Unresolved | linli | xuchengkai | xuchengkai | 08/Nov/17 11:09 AM |  | 29/Dec/17 1:07 PM |  |  | 1.22.1 |  |  | 0 | 2 | [16 empty] | None | [8 empty] | 8946
TrojanHorse | TROJ-2599 | 换皮机器的大厅机器方块图－五卷轴钻石 | Task | To Do | Major | Unresolved | linsen | xuchengkai | xuchengkai | 18/Dec/17 3:36 PM |  | 18/Dec/17 3:36 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9688
TrojanHorse | TROJ-2662 | 换皮包-大厅机器的方块图，5台 | Task | To Do | Major | Unresolved | linsen | xuchengkai | xuchengkai | 22/Dec/17 5:15 PM |  | 22/Dec/17 5:15 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9768
TrojanHorse | TROJ-2663 | 换皮包-大厅机器的方块图，5台 | Task | To Do | Major | Unresolved | linsen | xuchengkai | xuchengkai | 22/Dec/17 5:15 PM |  | 22/Dec/17 5:15 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9769
TrojanHorse | TROJ-2666 | 换皮包-大厅机器锁住时的框、jackpot奖金池、下载按钮和下载进度条 | Task | To Do | Major | Unresolved | linsen | xuchengkai | xuchengkai | 22/Dec/17 5:17 PM |  | 22/Dec/17 5:17 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9772
TrojanHorse | TROJ-2596 | 换皮机器的大厅机器方块图－转盘M10 | Task | To Do | Major | Unresolved | linsen | xuchengkai | xuchengkai | 18/Dec/17 3:34 PM |  | 29/Dec/17 1:16 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9685
TrojanHorse | TROJ-2432 | VIP机台解锁框 | Task | To Do | Major | Unresolved | linsen | 于笑晖 | 于笑晖 | 01/Dec/17 2:20 PM |  | 29/Dec/17 1:10 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9448
TrojanHorse | TROJ-2577 | 玩家玩着玩着credits丢失，玩家通过推送进入游戏后，筹码少了很多 | Bug | To Do | Critical | Unresolved | liuwen | Zhao Yunlong | Zhao Yunlong | 15/Dec/17 5:46 PM |  | 29/Dec/17 1:29 PM |  |  | 1.22.1 |  |  | 0 | 2 | _thumb_13335.png | [15 empty] | None | [8 empty] | 9660
TrojanHorse | TROJ-2622 | 换皮包-五卷轴机器1 | Task | To Do | Major | Unresolved | liuwen | 于笑晖 | xuchengkai | 22/Dec/17 11:34 AM |  | 22/Dec/17 11:35 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9726
TrojanHorse | TROJ-2580 | 五卷轴机器的逻辑 | Task | To Do | Major | Unresolved | liuwen | 于笑晖 | xuchengkai | 18/Dec/17 9:54 AM |  | 25/Dec/17 10:27 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9663
TrojanHorse | TROJ-2758 | 小猪银行ui层级永远显示在最顶端。 | Bug | In Review | Major | Unresolved | liuwen | ZhangXiang | ZhangXiang | 26/Dec/17 4:44 PM |  | 29/Dec/17 1:23 PM |  |  | 1.21.2 |  | 26/Dec/17 | 0 | 1 | [16 empty] | None | [8 empty] | 9872
TrojanHorse | TROJ-2570 | IOS Debug包240 进出M16时崩溃 | Bug | In Review | Major | Unresolved | liuwen | 沈怡澄 | 于笑晖 | 15/Dec/17 11:40 AM |  | 29/Dec/17 1:22 PM |  |  | 1.21.2 |  |  | 0 | 2 | [16 empty] | None | [8 empty] | 9645
TrojanHorse | TROJ-2378 | 付费打点bug | Bug | To Do | Major | Unresolved | liuwen | Zhao Yunlong | Zhao Yunlong | 30/Nov/17 6:13 PM |  | 29/Dec/17 1:29 PM |  |  | 1.22.1 |  |  | 0 | 1 | _thumb_13209.png | [7 empty] | start里面还是记录的9.99给40000 credits，但是由于玩家在购买过程中升级成了vip1，在success里面就显示给了44000 credits。而且此时有付费双倍credits的活动，玩家实际得到了80000credits。这里应该显示玩家实际得到的credits。 | [7 empty] | None | [8 empty] | 9394
TrojanHorse | TROJ-2685 | 换皮包-每日奖励，固定奖励的特效 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 22/Dec/17 5:43 PM | 29/Dec/17 1:59 PM | 22/Dec/17 5:43 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9790
TrojanHorse | TROJ-2761 | 给需要调整节奏的机器调整旋转节奏，现在机器配置表中可以单独配置旋转节奏了，如果不配置，就是默认节奏。 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 28/Dec/17 4:29 PM | 29/Dec/17 1:55 PM | 28/Dec/17 4:29 PM |  |  | 1.22.1 |  |  | 0 | 1 | [8 empty] | 机器配置表的Basic页中添加 SpinSpeed, NormalBlurFactor, HypeBlurFactor, 否则为默认值 | [7 empty] | None | [8 empty] | 9881
TrojanHorse | TROJ-2733 | 所有多线卷轴转动速度特别快 | Bug | To Do | Major | Unresolved | qiuyong | Yi Zhu | Yi Zhu | 23/Dec/17 7:37 AM | 29/Dec/17 1:59 PM | 28/Dec/17 4:29 PM |  | 1.23.2 | 1.22.1 |  |  | 0 | 1 | [8 empty] | 不确定是错觉还是bug，无论是哪个，都可以修复。 | [7 empty] | None | [8 empty] | 9838
TrojanHorse | TROJ-2661 | 换皮包-五图、icon，包括ios的iphone、ipad、iphone X适配，GP的phone、pad适配 | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 22/Dec/17 5:13 PM | 29/Dec/17 1:55 PM | 22/Dec/17 5:13 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9767
TrojanHorse | TROJ-2659 | 换皮包-大厅下方的Bar | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 22/Dec/17 5:12 PM | 29/Dec/17 1:55 PM | 28/Dec/17 6:29 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9765
TrojanHorse | TROJ-2660 | 换皮包-大厅背景、大厅公告牌框 | Task | To Do | Major | Unresolved | wangyaohan | xuchengkai | xuchengkai | 22/Dec/17 5:13 PM | 29/Dec/17 1:55 PM | 29/Dec/17 11:06 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9766
TrojanHorse | TROJ-2773 | 新水晶鞋，右边收集器的位置和卷轴框的右边重叠了（建议收集器下方的圆球做的小一点） | Bug | To Do | Major | Unresolved | wangyaohan | 沈怡澄 | 沈怡澄 | 29/Dec/17 1:52 PM | 02/Jan/18 9:41 AM | 29/Dec/17 3:04 PM |  |  | 1.21.2 |  | 29/Dec/17 | 0 | 1 | [16 empty] | None | [8 empty] | 9894
TrojanHorse | TROJ-1619 | 优化jackpot机制，不出现jackpot奖金比bet小的情况 | Task | In Review | Major | Unresolved | xuchengkai | Yi Zhu | Yi Zhu | 03/Oct/17 1:24 PM | 02/Jan/18 9:41 AM | 13/Dec/17 4:02 PM |  | 1.14.0 | 1.21.2 |  |  | 0 | 2 | [16 empty] | None | [8 empty] | 8329
TrojanHorse | TROJ-2735 | 整理经济系统的数据结果 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 25/Dec/17 10:25 AM | 29/Dec/17 3:59 PM | 25/Dec/17 10:25 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9840
TrojanHorse | TROJ-2727 | 换皮包-跟进新游上线奖励大厅公告、大厅机器、大厅机器解锁动、五图、icon、logo、loading界面 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 22/Dec/17 6:04 PM |  | 26/Dec/17 3:45 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9832
TrojanHorse | TROJ-2607 | 考虑添加SPIN时的卷轴特效 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 19/Dec/17 6:30 PM |  | 28/Dec/17 6:28 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9698
TrojanHorse | TROJ-2547 | 研究zenjoy三转盘玩法 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 11/Dec/17 3:36 PM |  | 29/Dec/17 9:50 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9600
TrojanHorse | TROJ-2718 | 换皮包-新游上线奖励弹窗的需求 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 22/Dec/17 6:00 PM |  | 29/Dec/17 9:52 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9823
TrojanHorse | TROJ-2717 | 更好地追踪免费筹码的需求 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 22/Dec/17 6:00 PM |  | 29/Dec/17 9:54 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9822
TrojanHorse | TROJ-2771 | 目前VIP机器的排列不太好，V1和V2、V3都是紫色，V4V5是金色。所以应该排成V1，V5，V2，V4，V3 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 29/Dec/17 12:48 PM | 29/Dec/17 2:01 PM | 29/Dec/17 12:48 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9892
TrojanHorse | TROJ-2728 | 换皮包-新公司账号，及商店设置 | Task | To Do | Major | Unresolved | Yi Zhu | xuchengkai | xuchengkai | 22/Dec/17 6:05 PM |  | 29/Dec/17 9:59 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9833
TrojanHorse | TROJ-2567 | 机台美术风格整理 | Task | To Do | Critical | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 15/Dec/17 11:26 AM | 02/Jan/18 9:44 AM | 28/Dec/17 6:06 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9642
TrojanHorse | TROJ-2704 | 换皮包-每小时奖励转盘的需求，程序、美术UI、特效、动画、数值 | Task | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 22/Dec/17 5:52 PM |  | 22/Dec/17 5:52 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9809
TrojanHorse | TROJ-2703 | 换皮包-种子筛选系统的需求，用来固定新玩家数值 | Task | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 22/Dec/17 5:51 PM |  | 22/Dec/17 5:51 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9808
TrojanHorse | TROJ-2705 | 换皮包-建立更精确的用户分群的需求 | Task | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 22/Dec/17 5:52 PM |  | 22/Dec/17 5:52 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9810
TrojanHorse | TROJ-2706 | 换皮包-设计整体数值 | Task | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 22/Dec/17 5:53 PM |  | 22/Dec/17 5:53 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9811
TrojanHorse | TROJ-2721 | 针对不同情况，设置不同的数值体验的需求 | Task | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 22/Dec/17 6:02 PM |  | 22/Dec/17 6:02 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9826
TrojanHorse | TROJ-2709 | 换皮包-跟进每小时奖励转盘、每日奖励、种子筛选系统、更精确的用户分群、提高广告变现 | Task | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 22/Dec/17 5:54 PM |  | 26/Dec/17 3:45 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9814
TrojanHorse | TROJ-2502 | 玩家关掉share to facebook选项后，再登录游戏，默认不选中share to facebook | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 06/Dec/17 5:35 PM |  | 28/Dec/17 6:07 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9529
TrojanHorse | TROJ-2338 | 根据用户分群进行弹窗控制，弹框控制优化文档 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 29/Nov/17 3:43 PM |  | 28/Dec/17 6:08 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9345
TrojanHorse | TROJ-2454 | 付费用户专门运营，付费用户流失行为分析 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 04/Dec/17 9:44 AM |  | 28/Dec/17 6:07 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9472
TrojanHorse | TROJ-2571 | 新游戏名称，关键词确定 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 15/Dec/17 11:41 AM |  | 28/Dec/17 6:07 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9646
TrojanHorse | TROJ-2375 | 用户分群活动，推送细化 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 30/Nov/17 4:24 PM |  | 28/Dec/17 6:08 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9389
TrojanHorse | TROJ-2455 | 用户分群量化分析 | Task | To Do | Major | Unresolved | Zhao Yunlong | Zhao Yunlong | Zhao Yunlong | 04/Dec/17 9:45 AM |  | 28/Dec/17 6:08 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9473
TrojanHorse | TROJ-2618 | 玩家收到邮件的神策打点需求 | Task | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 21/Dec/17 6:37 PM |  | 28/Dec/17 6:28 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9721
TrojanHorse | TROJ-1116 | 根据好友人数，增加每日奖励（调整UI、动画、逻辑） | Story | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 19/Jul/17 8:11 PM |  | 29/Dec/17 9:51 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 7538
TrojanHorse | TROJ-2626 | VIP机台-V3 | Task | To Do | Major | Unresolved | zhousen | 于笑晖 | xuchengkai | 22/Dec/17 11:37 AM |  | 22/Dec/17 11:37 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9730
TrojanHorse | TROJ-2625 | VIP机台-V2 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 11:37 AM |  | 22/Dec/17 11:37 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9729
TrojanHorse | TROJ-2634 | 换皮包-添加每日奖励，固定奖励的特效 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 1:54 PM |  | 22/Dec/17 1:54 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9739
TrojanHorse | TROJ-2629 | 换皮包-添加大厅机器方块图 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 11:57 AM |  | 22/Dec/17 11:57 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9734
TrojanHorse | TROJ-2654 | M19忍者主题，部分Wild播放动画时富士山消失 | Task | To Do | Major | Unresolved | zhousen | 于笑晖 | 于笑晖 | 22/Dec/17 5:10 PM | 02/Jan/18 9:42 AM | 22/Dec/17 5:10 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9760
TrojanHorse | TROJ-2762 | V5金盆主题的jackpot奖金池变成Freespin tips的时候，jackpot奖金池的UI先消失，流光特效后消失。 | Bug | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 29/Dec/17 11:23 AM |  | 29/Dec/17 11:23 AM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9883
TrojanHorse | TROJ-2768 | M6水晶鞋机器收集最后几个水晶鞋时，应先播放收集水晶鞋的动画，播放完之后再播放Freespin tips的动画。现在是同时播放的，不好 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 29/Dec/17 12:29 PM | 02/Jan/18 9:43 AM | 29/Dec/17 12:29 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9889
TrojanHorse | TROJ-2553 | 火主题机器，特效出现在buy credits按钮上了 | Bug | To Do | Major | Unresolved | zhousen | 沈怡澄 | 沈怡澄 | 12/Dec/17 4:34 PM |  | 29/Dec/17 1:10 PM |  |  | 1.21.2 |  | 12/Dec/17 | 0 | 3 | [16 empty] | None | [8 empty] | 9606
TrojanHorse | TROJ-2772 | 彩虹机台支付线图片缺失 | Bug | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 29/Dec/17 1:15 PM |  | 29/Dec/17 1:15 PM |  |  | 1.21.2 |  |  | 0 | 1 | _thumb_13362.png | [15 empty] | None | [8 empty] | 9893
TrojanHorse | TROJ-2621 | VIP机台-V1 | Task | To Do | Major | Unresolved | zhousen | 于笑晖 | xuchengkai | 22/Dec/17 11:32 AM |  | 29/Dec/17 1:24 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9725
TrojanHorse | TROJ-2770 | 忍者机器的wild的动画缺失 | Bug | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 29/Dec/17 12:38 PM |  | 29/Dec/17 1:39 PM |  |  | 1.21.2 |  |  | 0 | 1 | _thumb_13361.png | [15 empty] | None | [8 empty] | 9891
TrojanHorse | TROJ-2760 | 添加M34天使与魔鬼Freespin BGM，文件名：M34_Freespin.ogg | Task | In Review | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 27/Dec/17 4:44 PM | 02/Jan/18 9:41 AM | 29/Dec/17 1:47 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9878
TrojanHorse | TROJ-2759 | iPad适配-回流奖励界面下面遮罩没遮完全。 | Bug | In Review | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 27/Dec/17 3:25 PM |  | 29/Dec/17 1:44 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9876
TrojanHorse | TROJ-2586 | M31彩虹机器卷轴下遮罩遮框 | Bug | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 18/Dec/17 11:38 AM | 02/Jan/18 9:42 AM | 29/Dec/17 1:44 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9670
TrojanHorse | TROJ-2713 | 换皮包-五卷轴机器2需求，程序、美术UI、特效、动画、数值 | Task | To Do | Major | Unresolved | 于笑晖 | xuchengkai | xuchengkai | 22/Dec/17 5:56 PM |  | 22/Dec/17 5:56 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9818
TrojanHorse | TROJ-2715 | 换皮包-跟进卷轴界面上Bar、下方按键、锦标赛UI、大厅背景、大厅公告牌框、大厅下方的Bar | Task | To Do | Major | Unresolved | 于笑晖 | xuchengkai | xuchengkai | 22/Dec/17 5:58 PM |  | 26/Dec/17 3:45 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9820
TrojanHorse | TROJ-2714 | VIP机台-针对不同BET，设置不同的最大奖中奖倍数的需求 | Task | To Do | Major | Unresolved | 于笑晖 | xuchengkai | xuchengkai | 22/Dec/17 5:57 PM |  | 29/Dec/17 11:48 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9819
TrojanHorse | TROJ-2711 | 跟进VIP房间相关内容 | Task | To Do | Major | Unresolved | 于笑晖 | xuchengkai | xuchengkai | 22/Dec/17 5:54 PM |  | 29/Dec/17 11:38 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9816
TrojanHorse | TROJ-2436 | V3-钻石机台的跟进 | Task | To Do | Major | Unresolved | 于笑晖 | 于笑晖 | 于笑晖 | 01/Dec/17 2:29 PM |  | 29/Dec/17 1:08 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9452
TrojanHorse | TROJ-2394 | VIP系统的跟进 | Task | To Do | Major | Unresolved | 于笑晖 | 于笑晖 | 于笑晖 | 01/Dec/17 12:01 PM | 02/Jan/18 9:41 AM | 02/Jan/18 9:41 AM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9414
TrojanHorse | TROJ-2642 | 换皮包-卷轴界面上Bar，下方按键，锦标赛UI | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 22/Dec/17 1:59 PM | 29/Dec/17 1:54 PM | 22/Dec/17 1:59 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9747
TrojanHorse | TROJ-2590 | PayTable可以优化排版 | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 18/Dec/17 11:44 AM | 29/Dec/17 1:54 PM | 22/Dec/17 4:58 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9674
TrojanHorse | TROJ-2649 | V5金桶主题，背景偏暗，Freespin框偏亮 | Task | To Do | Major | Unresolved | 徐盛富 | 于笑晖 | 于笑晖 | 22/Dec/17 5:09 PM | 02/Jan/18 9:43 AM | 22/Dec/17 5:09 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9755
TrojanHorse | TROJ-2406 | VIP机台Paytable-V3 钻石机台 | Task | To Do | Major | Unresolved | 徐盛富 | 于笑晖 | xuchengkai | 01/Dec/17 12:52 PM | 29/Dec/17 1:54 PM | 25/Dec/17 1:36 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9424
TrojanHorse | TROJ-2749 | 篮球机器freespin框优化 | Task | To Do | Major | Unresolved | 徐盛富 | Zhao Yunlong | Zhao Yunlong | 25/Dec/17 5:28 PM | 29/Dec/17 1:53 PM | 25/Dec/17 5:28 PM |  |  | 1.22.1 |  |  | 0 | 1 | _thumb_13357.png | [15 empty] | None | [8 empty] | 9862
TrojanHorse | TROJ-2542 | 新手礼包的购买界面信息杂乱，金币图形抢文字内容 | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 11/Dec/17 2:59 PM |  | 28/Dec/17 6:21 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9595
TrojanHorse | TROJ-2540 | M5原创钻石机台卷轴框黑边面积过大（调整下） | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 11/Dec/17 2:56 PM |  | 28/Dec/17 6:21 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9593
TrojanHorse | TROJ-2473 | 篮球主题篮球symbol的白色描边可以弱化掉 | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 04/Dec/17 11:53 AM | 29/Dec/17 1:54 PM | 28/Dec/17 6:20 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9492
TrojanHorse | TROJ-2411 | 非节日的五图，替换圣诞节五图 | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 01/Dec/17 1:03 PM | 29/Dec/17 1:54 PM | 28/Dec/17 6:19 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9428
TrojanHorse | TROJ-2544 | M27无主题上方symbol有部分盖在卷轴上了，卷轴可以再高点。 | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 11/Dec/17 3:07 PM | 29/Dec/17 1:54 PM | 28/Dec/17 6:25 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9597
TrojanHorse | TROJ-2541 | 游戏内上方Bar上Level等级的投影效果太重 | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 11/Dec/17 2:58 PM | 29/Dec/17 1:54 PM | 28/Dec/17 6:30 PM |  |  | 1.22.1 |  |  | 0 | 2 | [16 empty] | None | [8 empty] | 9594
TrojanHorse | TROJ-2543 | BigWin和EpicWin计钱框优化 | Task | To Do | Major | Unresolved | 徐盛富 | xuchengkai | xuchengkai | 11/Dec/17 2:59 PM | 29/Dec/17 1:54 PM | 28/Dec/17 6:22 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9596
TrojanHorse | TROJ-2753 | 海盗机器，收集到三个宝藏图的时候，上方的freespin横幅动画有问题 | Bug | To Do | Major | Unresolved | 李馨媚 | 沈怡澄 | 沈怡澄 | 26/Dec/17 2:53 PM |  | 27/Dec/17 6:58 PM |  |  | 1.21.2 |  | 26/Dec/17 | 0 | 1 | [16 empty] | None | [8 empty] | 9867
TrojanHorse | TROJ-2341 | 新机器特效调优（周五讨论之后）-忍者主题 | Task | In Review | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 29/Nov/17 4:17 PM |  | 29/Dec/17 2:53 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9348
TrojanHorse | TROJ-2670 | VIP机台的特效-V2 | Task | In Review | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 22/Dec/17 5:28 PM |  | 29/Dec/17 2:53 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9776
TrojanHorse | TROJ-2669 | 机台特效-V1 | Task | In Review | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 22/Dec/17 5:27 PM |  | 29/Dec/17 2:53 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9775
TrojanHorse | TROJ-2600 | 换皮机器的大厅机器方块图－五卷轴 | Task | To Do | Major | Unresolved | 肖樊 | xuchengkai | xuchengkai | 18/Dec/17 3:37 PM |  | 18/Dec/17 3:37 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9689
TrojanHorse | TROJ-2667 | 换皮包五卷轴机器 | Task | To Do | Major | Unresolved | 肖樊 | 于笑晖 | xuchengkai | 22/Dec/17 5:17 PM |  | 22/Dec/17 5:17 PM |  |  | 1.22.1 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9773
TrojanHorse | TROJ-2668 | 换皮包-logo，换主色调 | Task | To Do | Major | Unresolved | 肖樊 | xuchengkai | xuchengkai | 22/Dec/17 5:19 PM |  | 22/Dec/17 5:19 PM |  |  | 1.21.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9774