## Sheet1
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Sprint | Epic Link | Epic Name | Epic Status | Epic Color | Flagged | Epic/Theme | Story Points | Business Value | Rank
TrojanHorse | TROJ-2702 | 换皮包-每小时奖励转盘的音效 | Task | To Do | Major | Unresolved | FangLei | xuchengkai | xuchengkai | 22/Dec/17 5:49 PM |  | 22/Dec/17 5:49 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9807
TrojanHorse | TROJ-2701 | 换皮包-每日奖励，固定奖励的音效 | Task | To Do | Major | Unresolved | FangLei | xuchengkai | xuchengkai | 22/Dec/17 5:49 PM |  | 22/Dec/17 5:49 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9806
TrojanHorse | TROJ-2639 | 换皮包-更精确的用户分群 | Task | To Do | Major | Unresolved | fanrongqi | Zhao Yunlong | xuchengkai | 22/Dec/17 1:57 PM | 29/Dec/17 1:51 PM | 22/Dec/17 1:57 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9744
TrojanHorse | TROJ-2664 | 换皮包-大厅机器的方块图，5台 | Task | To Do | Major | Unresolved | linsen | xuchengkai | xuchengkai | 22/Dec/17 5:15 PM |  | 22/Dec/17 5:15 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9770
TrojanHorse | TROJ-2687 | 换皮包-卷轴界面上Bar的特效、下Bar按键的特效，大厅下Bar的特效 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 22/Dec/17 5:44 PM | 29/Dec/17 1:59 PM | 22/Dec/17 5:44 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9792
TrojanHorse | TROJ-2775 | 换皮包-大厅方块图的特效，7个 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 29/Dec/17 1:58 PM | 29/Dec/17 2:00 PM | 29/Dec/17 1:58 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9896
TrojanHorse | TROJ-2683 | 换皮包-每小时奖励转盘的特效 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 22/Dec/17 5:42 PM | 29/Dec/17 1:59 PM | 29/Dec/17 1:59 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9788
TrojanHorse | TROJ-2680 | 换皮包-大厅公告牌边框特效 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 22/Dec/17 5:40 PM | 29/Dec/17 1:59 PM | 29/Dec/17 1:59 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9785
TrojanHorse | TROJ-2684 | 换皮包-每小时奖励可领取时的按钮动画特效 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 22/Dec/17 5:43 PM | 29/Dec/17 1:59 PM | 29/Dec/17 1:59 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9789
TrojanHorse | TROJ-2678 | 换皮包-大厅背景特效 | Task | To Do | Major | Unresolved | qiuyong | xuchengkai | xuchengkai | 22/Dec/17 5:37 PM | 29/Dec/17 1:59 PM | 29/Dec/17 1:59 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9784
TrojanHorse | TROJ-2726 | 换皮包-新商店描述 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 22/Dec/17 6:04 PM | 29/Dec/17 2:00 PM | 22/Dec/17 6:04 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9831
TrojanHorse | TROJ-2731 | 换皮包-广告单图的需求 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 22/Dec/17 6:06 PM | 29/Dec/17 2:00 PM | 22/Dec/17 6:06 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9836
TrojanHorse | TROJ-2730 | 换皮包-新Feedback接收邮箱 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 22/Dec/17 6:06 PM |  | 22/Dec/17 6:06 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9835
TrojanHorse | TROJ-2725 | 换皮包-机器单独配置旋转节奏、模糊度、旋转音效、背景音乐 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 22/Dec/17 6:04 PM |  | 29/Dec/17 9:52 AM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9830
TrojanHorse | TROJ-2501 | 大厅公告牌数量果多，导致下面的小点放不下的问题 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 06/Dec/17 5:19 PM | 29/Dec/17 2:01 PM | 29/Dec/17 1:11 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9528
TrojanHorse | TROJ-2769 | M6水晶鞋机器的wildx5公主的动画与wildx2王子数字动画节奏不统一 | Task | To Do | Major | Unresolved | xuchengkai | xuchengkai | xuchengkai | 29/Dec/17 12:33 PM | 29/Dec/17 2:01 PM | 29/Dec/17 2:01 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9890
TrojanHorse | TROJ-2707 | 换皮包-游戏商品的设计和添加 | Task | To Do | Major | Unresolved | Zhao Yunlong | xuchengkai | xuchengkai | 22/Dec/17 5:53 PM |  | 22/Dec/17 5:53 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9812
TrojanHorse | TROJ-2628 | 换皮包-添加大厅背景特效 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 11:56 AM | 02/Jan/18 9:45 AM | 22/Dec/17 11:56 AM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9733
TrojanHorse | TROJ-2637 | 换皮包-添加卷轴界面上Bar的特效、下Bar按键的特效，大厅下Bar的特效 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 1:56 PM |  | 22/Dec/17 1:56 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9742
TrojanHorse | TROJ-2638 | 换皮包-添加卷轴左边锦标赛的特效，沿用Huge Win Slots | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 1:56 PM |  | 22/Dec/17 1:56 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9743
TrojanHorse | TROJ-2755 | 圣诞节机器中，开关一下sound effect后，背景音乐缺失了 | Bug | To Do | Major | Unresolved | zhousen | 沈怡澄 | 沈怡澄 | 26/Dec/17 3:23 PM |  | 27/Dec/17 5:15 PM |  |  | 1.22.2 |  | 26/Dec/17 | 0 | 2 | _thumb_13360.png | [15 empty] | None | [8 empty] | 9869
TrojanHorse | TROJ-2015 | 游戏换皮需要用到的代码混淆器。 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 08/Nov/17 4:41 PM |  | 29/Dec/17 1:24 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 8950
TrojanHorse | TROJ-2630 | 换皮包-添加大厅机台解锁时的动画特效 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 11:58 AM |  | 29/Dec/17 1:34 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9735
TrojanHorse | TROJ-2632 | 换皮包-添加每小时奖励可领取时的按钮动画特效 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 1:53 PM |  | 29/Dec/17 1:39 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9737
TrojanHorse | TROJ-2627 | 换皮包-拼大厅，上下Bar、各种按钮、背景、大厅公告牌 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 11:56 AM |  | 29/Dec/17 1:36 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9732
TrojanHorse | TROJ-2633 | 换皮包-添加每小时奖励转盘的特效 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 1:54 PM |  | 29/Dec/17 1:39 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9738
TrojanHorse | TROJ-2631 | 换皮包-添加每小时奖励转盘 | Task | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 22/Dec/17 11:59 AM |  | 29/Dec/17 1:38 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9736
TrojanHorse | TROJ-1748 | 从GP商店和App Store下载的玩家获取邮箱。 | Story | To Do | Major | Unresolved | zhousen | xuchengkai | xuchengkai | 23/Oct/17 6:31 PM | 29/Dec/17 3:03 PM | 29/Dec/17 3:03 PM |  |  | 1.22.2 |  |  | 0 | 2 | [16 empty] | None | [8 empty] | 8599
TrojanHorse | TROJ-2672 | 换皮包-5卷轴机器1的特效 | Task | To Do | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 22/Dec/17 5:29 PM | 29/Dec/17 2:00 PM | 22/Dec/17 5:29 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9778
TrojanHorse | TROJ-2671 | VIP机台的特效-V3 | Task | To Do | Major | Unresolved | 李馨媚 | xuchengkai | xuchengkai | 22/Dec/17 5:28 PM |  | 22/Dec/17 5:28 PM |  |  | 1.22.2 |  |  | 0 | 1 | [16 empty] | None | [8 empty] | 9777